## excel
/Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Daniel Melgarejo
Start Date | may 01, 2017 08:25:34 PM
Completion Date | may 03, 2017 10:45:49 PM |  |  |  | Completed: *
Keywords
Language
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 18.2 | 32.2 | 28.7
Planned Time | 0.17292 |  | 0.75764
Actual Tiempo |  | 0.17222 | 1899-12-31 04:02
CPI (Cost-Performance Index) |  |  | 0.8
% Reuse | 18% | 16.1% | 16.4%
% New Reusable | 99.7% | 0% | 43.2%
Test Defects/KLOC or equivalent | 2.98 | 0 | 2.48
Total Defects/KLOC or equivalent | 20.8 | 15 | 18.6
Yield % | 85.7% | 100% | 92.9%
Code Review Rate | 420 | 499 | 619
% Appraisal COQ | 8.16% | 14.5% | 9.1%
% Failure COQ | 25.6% | 20.2% | 24.8%
COQ A/F Ratio | 0.32 | 0.72 | 0.37
PQI | 0.05 | 0.14 | 0.06
Program Size
| Plan | Actual | A la Fecha
Base (B) | 313 | 313 | 440
Deleted (D) | 0 | 0 | 20
Modified (M) | 10 | 15 | 28
Added (A) | 65.4 | 118 | 1206
Reused (R) | 83 | 83 | 318
Added and Modified (A+M) | 75.4 | 133 | 805
Total Size (T) | 461 | 514 | 1944
Total New Reusable | 75.2 | 0 | 348
Estimated Proxy Size (E) | 122 | 169 | 1415
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.022917 | 0.010417 | 0.14306 | 12.2%
DiseÃ±o | 0.015972 | 0.027083 | 0.12014 | 10.3%
RevisiÃ³n de DiseÃ±o | 0.0069444 | 0.013889 | 0.052083 | 4.46%
CodificaciÃ³n | 0.063194 | 0.066667 | 0.42917 | 36.7%
RevisiÃ³n de CodificaciÃ³n | 0.0076389 | 0.011111 | 0.054167 | 4.64%
CompilaciÃ³n | 0.011806 | 0.013194 | 0.080556 | 6.9%
Pruebas | 0.032639 | 0.021528 | 0.20903 | 17.9%
Postmortem | 0.0125 | 0.0083333 | 0.079861 | 6.84%
Total | 0.17292 | 0.17222 | 1899-12-31 04:02
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0.12 | 0 | 1 | 7.14%
PlaneaciÃ³n | 0.36 | 0 | 3 | 21.4%
DiseÃ±o | 0.48 | 1 | 5 | 35.7%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0.73 | 1 | 6 | 42.9%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 1.57 | 2 | 14
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0.11 | 0 | 1 | 6.67%
RevisiÃ³n de DiseÃ±o | 0.34 | 1 | 4 | 26.7%
CodificaciÃ³n | 0.79 | 1 | 7 | 46.7%
RevisiÃ³n de CodificaciÃ³n | 0.11 | 0 | 1 | 6.67%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.22 | 0 | 2 | 13.3%
Total | 1.57 | 2 | 15
After Development | 0.56 | 0 | 5
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 2.11 | 3 | 3.2
Defects/Hour - Code Review | 0.63 | 0 | 0.77
Defects/Hour - Compile | 0 | 0 | 0
Defects/Hour - Test | 0.29 | 0 | 0.4
DRL (DLDR/UT) | 7.36 | 7.53 | 8.03
DRL (Code Review/UT) | 2.18 | 0 | 1.93
DRL (Compile/UT) | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:08 PM el 3/05/2017